## Project Tracker
INSTITUTIONAL PROCESS IMPROVEMENT TRACKER
Last Updated: June 25, 2026
Project ID | Project Name | Department / Owner | Category | Priority | Start Date | Target Date | Actual End Date | Status | % Complete | Requirements | Key Deliverables | Milestones | Issues / Notes
PI-001 | Student Enrollment Workflow | Registrar / J. Smith | Process Redesign | High | 2025-01-15 | 2025-06-30 |  | In Progress | 65% | Map current enrollment steps; identify bottlenecks; obtain stakeholder sign-off | As-is process map; To-be process map; SOP document; Training guide | Kickoff (Jan 15) ✓ ¦ Discovery (Feb 28) ✓ ¦ Draft SOP (Apr 30) ✓ ¦ UAT (Jun 15) ¦ Go-Live (Jun 30) | Delay in IT sign-off for portal integration; escalated to CIO on May 3
PI-002 | Faculty Onboarding Standardization | HR / M. Patel | Policy | High | 2025-02-01 | 2025-07-31 |  | In Progress | 40% | Review existing onboarding docs; benchmark peer institutions; draft unified policy | Benchmark report; Policy draft; Checklist toolkit; Manager guide | Kickoff (Feb 1) ✓ ¦ Benchmarking (Mar 31) ✓ ¦ Draft Policy (May 31) ¦ Approval (Jul 15) ¦ Launch (Jul 31)
PI-003 | Budget Reporting Automation | Finance / R. Chen | Technology | Medium | 2025-03-01 | 2025-09-30 |  | In Progress | 20% | Define reporting requirements; select BI tool; configure dashboards; train users | Requirements doc; Vendor selection memo; Power BI dashboards; Training materials | Kickoff (Mar 1) ✓ ¦ Requirements (Apr 15) ✓ ¦ Tool Selection (May 31) ¦ Build (Aug 31) ¦ Go-Live (Sep 30) | Awaiting Procurement approval for Power BI license
PI-004 | FERPA Compliance Audit | Compliance / T. Davis | Compliance | High | 2024-11-01 | 2025-03-31 | 2025-03-28 | Completed | 100% | Conduct data access audit; review disclosure logs; remediate gaps; document findings | Audit report; Gap analysis; Remediation plan; Updated disclosure forms | Kickoff (Nov 1) ✓ ¦ Audit (Dec 31) ✓ ¦ Gap Analysis (Jan 31) ✓ ¦ Remediation (Mar 15) ✓ ¦ Report (Mar 28) ✓ | Closed. 3 minor gaps remediated; annual re-audit scheduled Nov 2025
PI-005 | IT Help Desk Ticket SLA Review | IT / K. Nguyen | Process Redesign | Medium | 2025-04-01 | 2025-08-31 |  | Not Started | 0% | Analyze historical ticket data; define SLA tiers; update escalation policy | Data analysis report; Revised SLA policy; Escalation matrix; Staff training deck | Kickoff (Apr 1) ¦ Data Analysis (May 31) ¦ Policy Draft (Jun 30) ¦ Training (Aug 15) ¦ Launch (Aug 31) | Pending resource allocation from IT Director
PI-006 | Research Grant Submission Process | Research Office / A. Lopez | Process Redesign | Low | 2025-05-15 | 2025-11-30 |  | Not Started | 0% | Interview PIs and grants staff; document pain points; propose streamlined workflow | Interview findings; Future-state workflow; Revised submission checklist | Kickoff (May 15) ¦ Interviews (Jun 30) ¦ Analysis (Aug 31) ¦ Draft (Oct 31) ¦ Pilot (Nov 30)

## Dashboard
PROJECT IMPROVEMENT – EXECUTIVE DASHBOARD
Auto-calculated from Project Tracker ¦ June 25, 2026
Total Projects |  | Completed |  | In Progress |  | Not Started |  | Avg % Complete
6 |  | 1 |  | 3 |  | 2 |  | 37.5%
STATUS BREAKDOWN |  |  |  |  | PRIORITY BREAKDOWN
Completed | 1 |  | 16.67% |  | High | 3 |  | 50%
In Progress | 3 |  | 50% |  | Medium | 2 |  | 33.33%
Not Started | 2 |  | 33.33% |  | Low | 1 |  | 16.67%
On Hold | 0 |  | 0%
Cancelled | 0 |  | 0%
⚠ OVERDUE PROJECTS (Target Date < Today & Status ≠ Completed)
Project ID | Project Name |  | Owner |  | Target Date |  | Status |  | % Complete
Use Excel's AutoFilter on the "Project Tracker" sheet (filter Target Date < Today AND Status ≠ Completed) to see overdue projects.

## Issue Log
ISSUE & RISK LOG
Issue ID | Project ID | Date Raised | Issue / Risk Description | Impact | Probability | Priority Score | Owner | Status | Resolution / Notes
ISS-001 | PI-001 | 2025-05-03 | IT sign-off delayed for portal integration | High | Medium | High / Medium | J. Smith (PM) | Open | Escalated to CIO on May 3. Follow-up meeting scheduled May 17.
ISS-002 | PI-003 | 2025-04-20 | Procurement approval pending for Power BI license | Medium | Low | Medium / Low | R. Chen (Finance) | Open | Submitted purchase request #4421. Est. approval May 31.
ISS-003 | PI-005 | 2025-04-01 | Resource not yet allocated by IT Director | High | High | High / High | K. Nguyen (IT) | Open | Discussed in April 15 steering meeting. Decision expected by May 15.

## Instructions
HOW TO USE THIS TRACKER
Project Tracker | • Each row = one improvement project. • Use the dropdown menus in Status, Priority, and Category columns. • Enter % Complete as a decimal (0.75 = 75%). • Milestones column: use ✓ to mark completed milestones. • Add new projects below the last filled row.
Dashboard | • Automatically recalculates from Project Tracker — no manual entry needed. • KPI cards update whenever you add or change project data. • Use AutoFilter on Project Tracker to identify overdue items.
Issue Log | • Log any issues or risks that arise during project execution. • Link each issue to a Project ID for traceability. • Update Status and Resolution columns as issues are resolved.
Color Coding | • Green rows = Completed projects. • Blue/white rows = Active or not-started projects. • Grey rows = Not Started projects. • Dashboard KPI cards reflect live counts.